## Sheet1
System Name | Food Ordering and Delivery System
Members: | Bausin, Kent Jose F.
Bongcaron, Joriz Symon L.
Solana, Raffy G.
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September
Tasks | Assignee | Date Started | Date Finished | Status | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Create 6 Funtions | Solana | 2024-08-28 | 2024-09-06 | Done
ERD | Bongcaron | 2024-08-31 | 2024-09-09 | Done
Creating UI | Bausin | 2024-08-30 | 2024-09-08 | Done
Integrate with DB | Bausin | 2024-08-22 | 2024-08-30 | Todo
Create Github Repository | Solana | 2024-09-20 | 2024-09-22 | Done
Restaurant | Bausin | 2024-08-20 | 2024-08-23 | Todo
Order
Payment
Customer
Delivery Driver
Menu